## Sheet1
Sr. No. | Affected URL | Vulnerability Name | CVE/CWE | Severity | 2nd Retest Status (29/06/2026) | Comments / Proof
1 | https://esp.documantra.in/organization/create | Blind Server-Side Request Forgery | CWE-918 | HIGH | CLOSED | Fixed: ssrfGuard blocks private/metadata IPs on organization logo. Proof: POST /organization/api/organization/create with logo http://169.254.169.254/ returns HTTP 400 — Invalid or disallowed logo URL. Verified 29-Jun-2026.
2 | https://esp.documantra.in/forgot-password https://esp.documantra.in/admin/forgot-password | Session Invalidation after password change | CWE-613 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
3 | https://esp.documantra.in/account/profile | Session Does not Expire after Email Change | CWE-613 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
4 | https://esp.documantra.in/forgot-password https://esp.documantra.in/admin/forgot-password | Weak Password Policy on Forget Password | CWE-1391 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
5 | https://esp.documantra.in/login https://esp.documantra.in/admin/login | Cleartext Transmission of Credentials | CWE-319 | MEDIUM | CLOSED | All login/forgot-password over HTTPS + HSTS (max-age=31536000). Proof: curl -sSI https://esp.documantra.in/login ¦ grep strict-transport-security; security-policy transportSecurity: https-required.
6 | https://esp.documantra.in/auth/api/auth/profile | HTML Injection | CWE-79 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
7 | https://esp.documantra.in/admin/subscription | Negative Value in Monthly Credits Parameter | CWE-840 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
8 | https://esp.documantra.in/admin/subscription | Price Parameter Tampering | CWE-840 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
9 | https://esp.documantra.in/admin/subscription | No Rate Limit on Add Payment | CWE-770 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
10 | https://esp.documantra.in/admin/templates | No Rate Limit on New Template Functionality | CWE-770 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
11 | https://esp.documantra.in/admin/pdf-tools/new | No Rate Limit on Add PDF Functionality | CWE-770 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
12 | https://esp.documantra.in/admin/forgot-password | Weak Password History Policy | CWE-521 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
13 | https://esp.documantra.in/login https://esp.documantra.in/admin/login | Missing Session Timeout | CWE-613 | MEDIUM | CLOSED | Session idle timeout 8 hours. Proof: security-policy sessionIdleTimeoutHours: 8; SESSION_IDLE_TIMEOUT_MS=28800000.
14 | https://esp.documantra.in/dashboard https://esp.documantra.in/admin/dashboard | Insecure Storage of Session in Local Storage | CWE-922 | MEDIUM | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
15 | https://esp.documantra.in/dashboard https://esp.documantra.in/admin/dashboard | User Information Disclosure via Local Storage | CWE-922 | MEDIUM | CLOSED | JWT in httpOnly cookies (accessToken / adminAccessToken). Proof: DevTools localStorage — no adminToken or accessToken after login.
16 | https://esp.documantra.in/ | Using Components with known vulnerability | CWE-1104 | LOW | PARTIAL | react-router-dom@6.30.4, axios@1.12.2, npm audit fix on admin build. Remaining vulns are dev/transitive toolchain — not shipped in production bundle.
17 | https://esp.documantra.in/login https://esp.documantra.in/forgot-password | User Enumeration | CWE-203, CWE-204 | LOW | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
18 | https://esp.documantra.in/e-sign/create | Improper Input Validation on Create Template | CWE-20 | LOW | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
19 | https://esp.documantra.in/auth/api/auth/profile https://esp.documantra.in/auth/api/auth/profile | Improper Input Validation | CWE-20 | LOW | CLOSED | Profile validation blocks HTML/script in fullname. Proof: PUT /auth/api/auth/profile with script tag in fullname returns HTTP 400 — Full name contains disallowed characters. Verified 29-Jun-2026.
20 | https://esp.documantra.in/admin/templates/ai/generate-stream | Verbose Error Disclosure in Assistant API | CWE-209 | LOW | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
21 | https://esp.documantra.in/auth-login | HTTP OPTIONS Method Enabled | CWE-346 | LOW | CLOSED | OPTIONS blocked on /auth-login. Proof: curl -X OPTIONS https://esp.documantra.in/auth-login returns HTTP 405.
22 | https://esp.documantra.in/dashboard https://esp.documantra.in/admin/dashboard | Missing Useful Security Headers | CWE-693 | LOW | CLOSED | nginx vapt-user/admin-spa-headers: HSTS, CSP, X-Frame-Options, nosniff, etc. Proof: curl -sSI https://esp.documantra.in/dashboard/ shows security headers. 29-Jun-2026.
23 | https://esp.documantra.in/dashboard https://esp.documantra.in/admin/login | Server Information Disclosure | CWE-200 | LOW | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
24 | https://esp.documantra.in/auth/api/auth/profile/email/send-otp | Server version disclosure through Error page | CWE-200 | LOW | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
25 | https://esp.documantra.in/dashboard https://esp.documantra.in/admin/dashboard | An adversary can trick a user into performing a sensitive operation by Clickjacking | CWE-1021 | LOW | CLOSED | Admin clickjacking fixed: X-Frame-Options DENY on /admin/index.html. Proof: curl -sSI https://esp.documantra.in/admin/index.html ¦ grep x-frame-options: DENY. 29-Jun-2026.
26 | https://esp.documantra.in/dashboard https://esp.documantra.in/admin/login | Overly Permissive Cross-Origin Resource Policy | CWE-942 | LOW | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
27 | https://esp.documantra.in/api | Custom 404 Error Page not Implemented | CWE-756 | LOW | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.
28 | https://esp.documantra.in | Use of Outdated HTTP Protocol Version (HTTP/1.1) | CWE-444 | LOW | CLOSED | HTTP/2 enabled (listen 443 ssl http2). Proof: curl -sSI https://esp.documantra.in/ shows HTTP/2.
29 | https://esp.documantra.in/login https://esp.documantra.in/admin/login | 2FA is not enabled | CWE-306 | LOW | CLOSED | User TOTP 2FA + 90d grace (requireTwoFaForLogin:true). Admin TOTP via Admin > Security (adminTwoFactorAuthenticationAvailable:true). Proof: security-policy API + 2FA verify-login endpoints.
30 | https://esp.documantra.in/login https://esp.documantra.in/admin/login | Concurrent Logins enabled | CWE-613 | LOW | CLOSED | Max 5 concurrent sessions. Proof: security-policy maxConcurrentSessions: 5.
31 | https://esp.documantra.in/login https://esp.documantra.in/admin/login | Autocomplete Feature Enabled for Sensitive Fields | CWE-522 | LOW | CLOSED | autocomplete=off on login password fields (user + admin). Proof: DevTools on /login and /admin/login.
32 | https://esp.documantra.in | Open Network Ports | CWE-200 | LOW | CLOSED | Verified unchanged — fix from 1st retest remains effective. Re-verified 29-Jun-2026.